## Cover Note
DUNBARTONSHIRE AND ARGYLL & BUTE VALUATION JOINT BOARD
ANNUAL SERVICE CALENDAR 2018-19
Due to the potential for it to be unwieldy and difficulty to read, the Annual Service Calendar for 2018/19 excludes some Service Plan items where they;
* and/or their timetables are included in the Reporting Framework
* are not time specific, are marked as 'ongoing' or are subject to agreement with external parties
* duplicate similar/same actions under another heading
* are continual or very regularly recurring porcesses

## Annual Calendar
DUNBARTONSHIRE AND ARGYLL & BUTE VALUATION JOINT BOARD ANNUAL SERVICE CALENDAR 2018-19
YEAR |  | 2018 | [39 empty] | 2019
| Week beginning | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH
Ref | ANNUAL SERVICE CALENDAR 2018-19 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25
3.1 | The Valuation Roll
3.1.1 | Recommence the maintenance of the Valuation Roll | bar: APRIL 2
3.1.1 (q) | Produce Valuation rolls and supply as required by statute | bar: APRIL 2 to MAY 14
3.1.1 (r) | Ingather all-Scotland connections data for IGTs | JUNE 4: And thereafter
3.1.2 (a)(d) | Negotiate and settle Revaluation appeals
3.1.2 (b) | Liaise with VAC Secretaries re the citation of Appeals | APRIL 2: As above - see established VAC dates
3.1.3 | Receive, negotiate, cite and dispose of running roll appeals | APRIL 2: In parallel with Revaluation appeals
3.1.4 (a) | Liaise with VAC Secretaries to schedule Hearing dates | bar: OCTOBER 1 to NOVEMBER 26
3.1.8 (d) | Liasie with Finance Departments re requirments of new legislation | APRIL 2: Ongoing from prior to April 2018
3.1.8 (f) | Contribute to P&M Review/Consultation | MAY 7: Timelines not yet known but due to report in Autumn
3.2 | Council Tax List
3.2.1(m) | Complete year-end procedures | bar: APRIL 2 to APRIL 9
3.2.1 (n) | Reconciliation of CT Valuation List with billing department records | bar: APRIL 2; JULY 2; OCTOBER 1; JANUARY 7
3.2.1 (o) | Produce and circulate revised Council Tax Lists | bar: MAY 7 to MAY 28
3.2.3 | Arrange and manage VAC Hearings | APRIL 2: See 3.1.2 and 3.1.4 above
3.3 | Electoral Registration
3.3.1(a) | Review canvass procedures, inc telephone, internet & door-to-door | bar: JUNE 25
3.3.1(d) | Provide canvass schedule for printing and mailing contract | bar: APRIL 2 to APRIL 23
3.3.1(e) | Confirm electronic voting requirements/system | bar: APRIL 16 to APRIL 30
3.3.1(f) | Recruit door-to door canvassers | bar: JUNE 11 to JULY 23
3.3.1(g) | Train door-to door canvassers | bar: SEPTEMBER 3 to SEPTEMBER 10
3.3.1(h) | Obtain attainer information and populate EROS | APRIL 2: Quarterly by arrangement with the three councils
3.3.1(i) | Prepare files for canvass, including telephone and internet | bar: JUNE 11
3.3.1(j) | Issue HEFs, follow-up ITRs and Reminders | bar: JULY 2 to NOVEMBER 26
3.3.1(l) | Complete door-to-door canvass | bar: SEPTEMBER 10 to OCTOBER 29
3.3.1(m)(n)(p) | Record, scan, reference and process changes | bar: JULY 2 to NOVEMBER 26
3.3.1(o)(p) | Receive electronic returns & process as above | bar: JULY 2 to NOVEMBER 26
3.3.1(q) | Provide Senior Managers with canvass progress reports | bar: JULY 2 to NOVEMBER 26
3.3.1(r) | Produce and publish ‘Full/Electoral’ and ‘Edited/Open’ Registers | FEBRUARY 4: Possible Republication for WDC
3.3.1(s) | Supply of Registers to appropriate bodies/public display | APRIL 2: Following canvass and at monthly updates
3.3.1(v)(w) | Performance statistics to be supplied to EC and CO | bar: DECEMBER 3 to DECEMBER 10
3.3.2 (a)-(m) | Maintenance of the Electoral Register | APRIL 2: In accordance with Rolling Registration timetable issued annually
3.3.2(d) | Door-to-door canvass for HEF/ITR non-responses (o/with canvass) | APRIL 2: As required
3.3.2 (o) | Triennial enquiry to proxy voters | bar: APRIL 2 to JULY 23; JANUARY 14 to MARCH 4
3.3.2(r) | Review Participation Strategy/Activities
3.3.3 | Elections (See details of steps to be taken in main Service Plan) | APRIL 2: Only if called
3.3.3(j) | Receive report from ROs regarding failed AVs | APRIL 2: Only if relevant election held
3.3.3 (k)(l) | Issue letters re 3.3.3(j) above and process returns | APRIL 2: Only if relevant election held
3.3.3(m) | Ensure caveats are renewed | bar: MARCH 4 to MARCH 25
3.3.4/5(g) | Issue 5-yearly refresh of PIs for Absent Voters and process return | bar: JANUARY 7 to JANUARY 28
3.3.6(d) | Collate and submit ‘needs based’ claim for funding to Cabinet Office | bar: DECEMBER 3 to JANUARY 28
3.3.7(b) | Effect reviews of Polling Districts and Places | JANUARY 7: Probable implementation for WDC
3.4 | Corporate Governance
3.4.1(b)(c ) | Board meetings | JUNE 25: 29th
3.4.2(a)(b) | Arrange Board and Agenda meetings | APRIL 2: To be arranged to suit members/office bearers
3.4.2 (d) | Appoint Authors and prepare Reports | bar: MAY 7 to MAY 28
3.4.2(e ) | Publish Joint Board papers on DABVJB Web site | bar: JUNE 4 to JUNE 11
3.4.3(f) | Check RICS membership of professional staff | bar: MAY 7 to MAY 28
3.4.4(b) | Review 3-year Service Plan and Annual Calendar for 2019/20 | bar: FEBRUARY 4 to MARCH 25
3.4.5(a) | Review Corporate Governance Statement | bar: SEPTEMBER 3 to SEPTEMBER 24
3.4.5(b)(c ) | Review Fraud and Defalcation Procedures | bar: JUNE 4 to JUNE 25
3.4.5(f) | Corporate Governance 2017 Self-assessment actions | APRIL 2: See various timetables for completion
3.4.5(g) | Carry out 2018 Governance Self-assessment | bar: SEPTEMBER 3 to OCTOBER 22
3.4.7 | Management Team Meetings | APRIL 2: To be timetabled as appropriate
3.4.7(b) | Review Vision and Mission Statements | bar: MARCH 4 to MARCH 25
3.4.7 (c) | Communicate revised Vision & Mission Statements to staff | bar: MARCH 4 to MARCH 25
3.4.8 | Performance Management, Planning and Reporting | APRIL 2: Various schedules
3.4.8(a)-(c ), (h) | Set and Agree KPI targets (and provide to Scottish Government) | bar: APRIL 9 to APRIL 30; JUNE 4 to JUNE 25
3.4.8(i) | Review compliance with standard and submit EC performance stats | MAY 7: Review compliance in advance of canvass; OCTOBER 15: Canvass Survey; NOVEMBER 26: Submit stats
3.4.8(k) | Present KPI targets to Joint Board for approval | bar: JUNE 25
3.4.8(m) | Public Performance Report and Annual Report | bar: MAY 21 to MAY 28
3.4.10(g) | Check driving licences, insurances and MOTs | APRIL 2: Rolling checks for annual renewals
3.4.11(a) | Present Annual Accounts for external audit | bar: MAY 28
3.4.11(b)(c) | Agree Audit Plan with Auditors | APRIL 2: By arrangement - normally around February
3.4.12(a) | Review Risk Management Policy | bar: MAY 7 to JUNE 25
3.4.12(b)(c) | Review Risk Register and Action Plan | bar: FEBRUARY 4 to FEBRUARY 25
3.4.12(d) | Monitor progress against Risk Action Plan | APRIL 2: As per MTM Timetable
3.4.12(e) | Review Business Continuity/Disaster Recovery Plan | bar: MAY 7 to MAY 28
3.4.12(f) | Liaise with WDC Legal advisors to review all insurances | bar: JUNE 4 to JULY 30
3.4.12 (g) | Review various Electoral Risk Registers/Action Plans | APRIL 2: Various - annually
3.4.12(h) | Review ICT systems Risk Registers/Action Plans | bar: MAY 14 to MAY 28
3.5 | Accountability
3.5.1 (c ) | Pass Accruals Forms to Creditors section, WDC Finance | bar: APRIL 2
3.5.1(e)(f) | Revenue Accounts and Financial Statements to be finalised | bar: MAY 14 to MAY 28
3.5.1(g) | Annual Report Produced | bar: MAY 28
3.5.1(h) | First Public Inspection of accounts | bar: JULY 2 to AUGUST 27
3.5.1(i) | Final Audit Reports and Audit Certificates to be received | bar: SEPTEMBER 10
3.5.1(j) | Board/Finance Sub-Com to approve the audited financial statements | APRIL 2: Date to be confirmed at June Board meeting
3.5.1(k) | Submission of Annual Report and Accounts to Audit Commission | bar: SEPTEMBER 24
3.5.1(l) | Final Public Inspection (including adverts in local newspapers) | APRIL 2: By arrangement of Treasurer
3.5.3 (e ) | Provide Joint Board with Internal Audit Report on Appeals Processes | bar: JUNE 25
3.5.3(f) | Effect the recommendations of internal audit into appeals processes | APRIL 2: By September and various Timetables
3.5.4(c) | Report KPIs to Scottish Government (via SAA) | bar: JUNE 4 to JUNE 25
3.5.4(d) | Produce and publish Public Performance Reports | bar: JUNE 25
3.5.4(e) | Produce and return CIPFA Rating Review Budget figures to WDC | bar: APRIL 9 to MAY 7
3.5.4(f) | Produce and report (RVAPP) to Scottish Government | APRIL 2: 6th
3.5.4 (h) | Produce and return COSLA Joint Staffing Watch Survey | bar: APRIL 9 to APRIL 23; JULY 2 to JULY 9; OCTOBER 1; JANUARY 7
3.6 | Best Value
3.6.3(b) | Submit PPRs to Joint Board | APRIL 2: 1st meeting after compilation
3.6.3 (c ) | Publish PPRs in DAB website etc | bar: JUNE 11
3.6.4(b) | Review revised Customer Consultation procedures | APRIL 2: Ongoing from implementation in April 2018
3.4.6(d) | Prepare Customer Satisfaction Reports for MT | bar: APRIL 16 to MAY 14; OCTOBER 1 to OCTOBER 29
3.6.4(h) | Complete a Staff Satisfaction Survey | bar: JUNE 4 to AUGUST 6
3.6.4(i) | Complete door-to-door Canvasser survey | bar: DECEMBER 3 to DECEMBER 31
3.6.5(a) | Implement new procedures for recording Comments and Complaints | bar: APRIL 2
3.6.5(b)-(d) | Customer Comment and Complaints reports for Management Team | APRIL 2: As per MTM schedule
3.6.5(e ) | Publish lessons learned from Complaints | bar: APRIL 2 to APRIL 9; JULY 2 to JULY 9; OCTOBER 1 to OCTOBER 8; JANUARY 7 to JANUARY 14
3.6.5 (f) | Report Customer Comment and Complaint outcomes to Ombudsman | bar: APRIL 2 to APRIL 30
3.6.6(b) | Report Customer Service (Mail) performance to Management Team | bar: APRIL 9 to APRIL 23; OCTOBER 1 to OCTOBER 22
3.7 | Equal Opportunities
3.7.1(f) | Complete/update staff Equalities/Protected characteristics Survey | bar: JANUARY 7 to FEBRUARY 25
3.7.1(g) | Publish Equality Mainstreaming, Outcomes and Staffing report | APRIL 2: No requirement for publication of report in April 2018
3.7.2(b) | Review Equality Action Plan | APRIL 2: Various timetables
3.7.2(d) | Review Equality Targets/Goals/Outcomes | APRIL 2: No requirement to review Outcomes in 2018/19
3.7.3(d) | Include summaries of Equalities Reports in Public Performance Reports | bar: MAY 21 to MAY 28
3.7.3(e) | Include summaries of Equalities Reports in Annual Reports | bar: MAY 21 to MAY 28
3.7.4(c) | Provide Language Line training, including refresher training | APRIL 2: Individually timetabled in accordance with Core Training requirements
3.7.4(e) | Review Equal Opportunities training requirements at T&D reviews | bar: FEBRUARY 4 to FEBRUARY 25
3.8 | Staffing & Personnel Matters
3.8.1 | Reviews of various HR&OD Policies now due | APRIL 2: Various schedules for completion and approval
3.8.1 (e) | Review Health and Safety Policy | bar: OCTOBER 1 to OCTOBER 29
3.8.2(a) | Training and Development review meetings | AUGUST 6: Interim meetings
3.8.2(e) | Revise budget provision for training | bar: NOVEMBER 5 to DECEMBER 31
3.8.2(f) | Review Training and Development policy to align with business needs
3.8.2(p) | Complete Core Training Modules | APRIL 2: Annually and in advance of PDO meetings
3.8.3(a) | Issue, collect and analyse staff questionnaires | bar: JUNE 4 to JULY 30
3.8.3(b) | Follow up questionnaire results/outcomes where appropriate | bar: AUGUST 6 to AUGUST 27
3.8.3(c ) | Report outcomes to Management Team and agree actions | bar: SEPTEMBER 3 to SEPTEMBER 24
3.8.3(d) | Consider budgetary implications of agreed actions | bar: NOVEMBER 5 to DECEMBER 31
3.8.3(e) | Report outcomes and actions to staff | bar: AUGUST 6 to AUGUST 27
3.8.3(i) | Recruit to fill vacant post(s)
3.8.5(c )(d) | Revise H&S Risk Assessments and Action Plans | bar: OCTOBER 1 to OCTOBER 29
3.8.5(f) | Complete Stress Risk Assessment Survey | bar: APRIL 2 to APRIL 30; OCTOBER 1 to OCTOBER 29
3.9 | Finance & Budgeting
3.9.1(c ) | Review guidance to staff to reflect changes to Fin Regs and SOs | APRIL 2: As required by any review of Fin Regs or SOs
3.9.2(a) | Review probable out-turn and future requirements | bar: NOVEMBER 5 to JANUARY 28
3.9.2(b) | Prepare and agree provisional Revenue Budget Bid | bar: JANUARY 7 to JANUARY 28
3.9.2(c ) | Prepare and agree provisional Capital Budget Bid | bar: JANUARY 7 to JANUARY 28
3.9.2(d) | Seek approval for proposed budgets from Valuation Joint Board | bar: FEBRUARY 25
3.9.2(e) | Prepare detailed report on make up of Budget | bar: FEBRUARY 25 to MARCH 25
3.9.3(a) | Review & Implement procedures for Ordering, Invoicing and Payment | APRIL 2: As required by any Policy change
3.9.6 | Financial Monitoring Reports (internal) | APRIL 2: Monthly on receipt and in accordance with MTM schedule - See Reporting Framework
3.9.7 | Annual Accounts | APRIL 2: See 3.5.1 above - to be carried out in accordance with WDC timetable and completed by end May
3.10. | Information Technology
3.10.1(d) | Complete Review of ICT Strategy | bar: SEPTEMBER 3 to SEPTEMBER 24
3.10.2(a) | Review PCs and hardware for replacement | bar: NOVEMBER 5 to DECEMBER 31
3.10.2(b) | Investigate options & costs for procurement via WDC ICT | bar: NOVEMBER 5 to DECEMBER 31
3.10.2(c ) | Consider operational requirements and prioritise purchase plan | bar: NOVEMBER 5 to DECEMBER 31
3.10.2(d) | Complete Capital Budget Bid and submit to Joint Board | bar: JANUARY 7 to FEBRUARY 25
3.10.2(g) | Complete assessment, procure and implement contingency for EMS | APRIL 2: Dependent on assessment of need and dependencies on WDC and Idox/Halarose
3.10.2(h) | Procure and install new flexi-time system including new server | APRIL 2: Subject to ongoing assessment of requirement and market availability
3.10.4(a) | Complete new Data Protection Notification to ICO | bar: APRIL 23 to MAY 28; SEPTEMBER 3 to SEPTEMBER 24
3.10.4(b) | Review of Forms to comply with GDPR (Privacy Notices) | bar: APRIL 23 to MAY 28; SEPTEMBER 3 to SEPTEMBER 24
3.10.4(c ) | Review Data Processor Agreement with WDC | bar: APRIL 23 to MAY 28; SEPTEMBER 3 to SEPTEMBER 24
3.10.4 (d) | Implement or Review Data Sharing Agreements | JUNE 4: And ongoing
3.10.4(e) | Prepare for the new General Data Protection Regulation | APRIL 2: See above
3.10.5(a) | Review functionality of Freedom of Information logging system | bar: JANUARY 7 to JANUARY 28
3.10.5(b) | Prepare reports on FoI requests, refusals etc to Management Team | bar: JANUARY 7 to JANUARY 28
3.10.5 (c) | Prepare reports on FoI and submit to Information Commissioner | bar: APRIL 2 to APRIL 9; JULY 2 to JULY 9; SEPTEMBER 3 to SEPTEMBER 10; JANUARY 7 to JANUARY 14
3.10.6(c ) | Review and (if required) redevelop Progress appeals system | APRIL 2: Dependent on requirements of Valuation Working Group
3.10.8(a)(c ) | Attend EROS II User Group/SHUG meetings | bar: JULY 2; JANUARY 21 to JANUARY 28
3.10.8(d) | Implement upgraded versions of EROS, | APRIL 2: On receipt
3.10.9(c ) | Review use and functionality of Time Management System | bar: MAY 14 to MAY 28
3.10.9(e) | Provide Management Team with Customer Satisfaction Reports | bar: APRIL 23 to MAY 14; OCTOBER 8 to NOVEMBER 5
3.10.9(f) | Review use and functionality of Customer Satisfaction Database | APRIL 2: The new system will be under constant review following implementation in April 2018
3.10.9(h) | Refresh Mail Logging system and report performance | bar: APRIL 2 to MAY 7
3.10.11(a) | Review web site platform and content | bar: APRIL 2 to JUNE 25
3.10.12 | Review use fof Intranet site for policy documents, revised access levels | APRIL 2: Ongoing
3.10.13(a)(b) | Further develop and expand use ofshared directory structure | APRIL 2: Ongoing
3.10.13(c) | Close down other, non-controlled, shared directories | APRIL 2: TBC
3.11 | Freedom of Information
3.11.2(a) | Review FoI Policy, Publication Scheme and Guide to Information | bar: MAY 7 to MAY 28
3.11.2(b) | Review content of publications contained in Publication Schemes | APRIL 2: Continual
3.11.3 | Review information Audit & Staff Guidance (to follow above) | bar: JUNE 4 to JUNE 25
3.11.3 (g) | Report to Information Commissioner re FOI requests received | bar: APRIL 2 to APRIL 9; JULY 2 to JULY 9; OCTOBER 1 to OCTOBER 8; JANUARY 7 to JANUARY 14
3.12 | Key Partnerships
Most are subject to variable timetables or external agreement
3.12.1(h) | Budget planning meetings with Treasurer/Accountants | bar: DECEMBER 3 to JANUARY 28
3.12.1(l) | Attend WDC Senior Manager’s Network meetings
3.12.2 (b) | Provide reconcilliation files and follow-up meetings where required | bar: APRIL 2 to APRIL 9; JULY 2 to JULY 9; OCTOBER 8 to OCTOBER 22; JANUARY 14
3.12.2(e) | Attend Election Management/RO meetings | APRIL 2: As timetabled locally
3.12.3(a) | Attend SAA Plenary Meetings | MAY 28: 23-25
3.12.4(a) | Attend Harmonisation meeting | MAY 7: 8-9th
3.12.5(a) | AEA AGM and Conference | bar: JANUARY 14
3.12.5(b) | Plenary Meetings of Scottish Branch of AEA | bar: JUNE 4; MARCH 11
3.13 | Records Management
3.13(a) | Implement Improvement Action Plan locally | APRIL 2: Ongoing
3.13(d) | Consider self-assessment template and complete as appropriate | APRIL 2: When invited
3.14 | Miscellaneous
3.14.3(a) | Revise Data Protection Policy | bar: APRIL 2 to MAY 21
3.14.3(b) | Appoint a Data Protection Officer | bar: APRIL 30 to MAY 21
3.14.3 (c ) | Revise and implement Privacy Notices | bar: APRIL 2 to MAY 21
3.14.3(d) | Complete Personal Data Audit | bar: APRIL 2 to MAY 21
3.14.3(e ) | Provide Training and Guidance to staff re GDPR | bar: APRIL 30 to MAY 21